## READ ME FIRST
Quarterly Initiative Update - WMP Initiative Status Updates
Instructions for use
1 | Update progress on WMP Initiatives on "Initiatives" sheet by populating columns A through AB. Progress currently filled in is an example. Yellow cells indicate information that needs to be filled out or confirmed by utility. WMP initiatives that are not already listed in the "Initiatives" sheet shall be added as separate line items on the "Initiatives" sheet. Quantitative information, included initiative targets, the units of said targets and subsequent progress are reported in columns L through U with qualitative targets and progress described in columns V through Z.
2 | WSD Compliance will reach out to follow up on which Initiatives require documentation for auditing, indicated in columns AD and AE in the "Initiatives" sheet. For those initiatives requiring audit documentation, please fill out columns AF through AH. Please be sure to link to a Kiteworks folder in column AF.
3 | Definitions for each field are provided in the table below starting in row 17 - READ BEFORE INPUTTING DATA
4 | WSD Compliance will contact the electrical corporation with any follow-up questions regarding audits
Update the below table to establish which year, quarter, month of the WMP cycle this submission represents
Utility |  | SCE
Report Year |  | 2021
Report Quarter |  | Q3
Submission Date |  | 2021-11-02
Definition of fields
| Column | Column name | Definition | Input type | Submission in which to be completed
| A | UtilityID | Standardized ID of utility (PGE, SCE, SDGE, BVES, LU, PC, HWT, or TBC) - auto populated by utility field above | Text | Q1
| B | Submission Date | Autogenerated based on submission date field above | Date | Q1
| C | WMPInitiativeCategory | One of the 10 initiative categories in the WMP | Text | Q1
| D | WMPInitiativeCategory# | Autogenerated based on initiative category | Numeric | Q1
| E | WMPInitiativeActivity | The relevant WMP activity classification for the initiative. If this initiative applies to an activity not presented, mark "other" | Text | Q1
| F | ActivityNameifOther | If activity was "other", then provide the name of the appropriate activity. Should match an activity name in utility's WMP (Table 12) | Text | Q1
| G | WMPInitiativeActivity# | Autogenerated based on initiative activity. Will be number or name of activity if activity was marked as "other" | Numeric/Text | Q1
| H | UtilityInitiativeName | Utility name for initiative | Text | Q1
| I | InitiativeActivityID | ID for the utility initiative. Must be unique to a utility's Initiative activity across submissions. If this initiative is also reported in the initiatives feature class for Grid hardening, Asset inspections, or vegetation management and inspections, then this ID should also connect to the ID in the corresponding initiative feature class (Fields "GhlogID", "AiLogID", "VmiLogID", "VmpLogID", and "OiLogID") | Text | Q1
| J | WMPInitiativeCode | Unique ID of the initiative. Must be unique for each initiative for each utility for each year. Follows the format “[UtilityID]_ [WMPInitiativeCategory]_[ WMPInitiativeActivity]_[InitiativeActivityID]_[Year four digit number (e.g., “2021”)]”. For example the code “PGE_Vegetation Management & Inspections_Substation vegetation management _001_2021” would be where utility is PG&E, Initiative category is Vegetation Management & Inspections, activity is Substation vegetation management, unique initiative ID is 001 and the year is 2021 | Text | Q1
| K | WMPPageNumber | Page of most recent WMP where initiative is detailed. If the initiative is detailed on multiple pages, put the first page | Numeric | Q1
| L | QuantTargetUnits | If initiative has a quantitative target, then report the units for the target. For example, if the initiative is installing covered conductors, then the unit would be "# of covered conductors installed" | Text | Q1
| M | AnnualQuantTarget | Quantitative target for year | Numeric | Q1
| N | ProjectedQuantProgressQ1 | Quantitative projected progress by end of Q1: Jan 1 - Mar 31 | Numeric | Q1
| O | ProjectedQuantProgressQ1-2 | Cumulative quantitative projected progress by end of Q2: Jan 1 - June 30. Q1 projected progress + Q2 projected progress | Numeric | Q1
| P | ProjectedQuantProgressQ1-3 | Cumulative quantitative projected progress by end of Q3: Jan 1 - Sep 30. Q1 projected progress + Q2 projected progress + Q3 projected progress | Numeric | Q1
| Q | ProjectedQuantProgressQ1-4 | Cumulative quantitative projected progress by end of Q4: Jan 1 - Dec 31. Equal to total annual target | Numeric | Q1
| R | QuantActualProgressQ1 | Quantitative progress by end of Q1: Jan 1 - Mar 31 | Numeric | Q1
| S | QuantActualProgressQ1-2 | Cumulative quantitative progress by end of Q2: Jan 1 - June 30. Q1 progress + Q2 progress | Numeric | Q2
| T | QuantActualProgressQ1-3 | Cumulative quantitative progress by end of Q3: Jan 1 - Sep 30. Q1 progress + Q2 progress + Q3 progress | Numeric | Q3
| U | QuantActualProgressQ1-4 | Cumulative quantitative progress by end of Q4: Jan 1 - Dec 31. Total annual progress | Numeric | Q4
| V | QualTargetAnnual | If initiative has a qualitative target, then detail the target. For example, if the initiative is building a centralized data lake, then the target may be "Developing a centralized data lake by end of year" | Text | Q1
| W | QualProgressQ1 | Qualitative progress by end of Q1: Jan 1 - Mar 31 | Text | Q1
| X | QualProgressQ1-2 | Qualitative progress by end of Q2: Jan 1 - June 30 | Text | Q2
| Y | QualProgressQ1-3 | Qualitative progress by end of Q3: Jan 1 - Sep 30 | Text | Q3
| Z | QualProgressQ1-4 | Qualitative progress by end of Q4: Jan 1 - Dec 31. Total annual progress | Text | Q4
| AA | Status | Status of initiative, can be one of the following: Completed/In Progress/Planned/Delayed/Cancelled | Text | Q1, Q2, Q3, Q4
| AB | CorrectiveActionsIfDelayed | If initiative is delayed based on reported target vs progress (e.g., reported QuantProgress for Q1 was significantly below the ProjectedQuantProgress for Q1), detail corrective actions | Text | As needed
AC-onwards is managed by WSD; columns AF-AH will only be completed by utility upon WSD request

## Initiatives
UtilityID | Submission Date | WMPInitiativeCategory | WMPInitiativeCategory# | WMPInitiativeActivity | ActivityNameifOther | WMPInitiativeActivity# | UtilityInitiativeName | InitiativeActivityID | WMPInitiativeCode | WMPPageNumber | QuantTargetUnits | AnnualQuantTarget | ProjectedQuantProgressQ1 | ProjectedQuantProgressQ1-2 | ProjectedQuantProgressQ1-3 | ProjectedQuantProgressQ1-4 | QuantActualProgressQ1 | QuantActualProgressQ1-2 | QuantActualProgressQ1-3 | QuantActualProgressQ1-4 | AnnualQualTarget | QualActualProgressQ1 | QualActualProgressQ1-2 | QualActualProgressQ1-3 | QualActualProgressQ1-4 | Status | CorrectiveActionsIfDelayed | REFERENCE: Compliance Branch Requirements --> | Audit | Audit File Documentation Requested | FolderLink | PersonInChargeName | PersonInChargeEmail | Change Order | Change Order Status
SCE | 2021-11-02 | Risk Assessment & Mapping | 7.3.1 | Risk Assessment and Mapping Initiatives |  | 1 | N/A | N/A | SCE_Risk Assessment & Mapping_Risk Assessment and Mapping Initiatives_N/A_2021 | 189 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Risk Assessment & Mapping | 7.3.1 | Climate-driven risk map and modelling based on various relevant weather scenarios |  | 2 | N/A | N/A | SCE_Risk Assessment & Mapping_Climate-driven risk map and modelling based on various relevant weather scenarios _N/A_2021 | 193 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Risk Assessment & Mapping | 7.3.1 | Initiative mapping and estimation of wildfire and PSPS risk-reduction impact |  | 4 | N/A | N/A | SCE_Risk Assessment & Mapping_Initiative mapping and estimation of wildfire and PSPS risk-reduction impact _N/A_2021 | 194 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Situational Awareness & Forecasting | 7.3.2 | Advanced weather monitoring and weather stations |  | 1 | Weather Stations | SA-1 | SCE_Situational Awareness & Forecasting_Advanced weather monitoring and weather stations _SA-1_2021 | 196 | # of weather stations installed | SCE expects to install 375 weather stations but will attempt to install as many as 475. | 0 installations. Preparation work for Q2 ramp up. | 120 installations | 375 installations | 375 installations | Preparation work for 2021 installations conducted in Q1. Installations to begin in Q2. | ~100 installations. Expect ramp up in Q3. | ~375 installations in Q3 |  | N/A |  |  |  |  | Completed | [7 empty] | No
SCE | 2021-11-02 | Situational Awareness & Forecasting | 7.3.2 | Continuous monitoring sensors |  | 2 | Distribution Fault Anticipation (DFA) | SA-9 | SCE_Situational Awareness & Forecasting_Continuous monitoring sensors _SA-9_2021 | 198 | # of units on circuits | Complete installation of 120 DFA units on circuits in SCE’s HFRA and continue evaluation of DFA technology which may result in SCE installing up to 150 units | 0 installations. Preparation work for Q3 ramp up. | 0 installations. Preparation work for Q3 ramp up. | 73 installations | 120 installations | Devices are in design with installations to begin in Q3. | Devices are in design with installations to begin in Q3. | 87 DFA devices have been installed ahead of planned dates but are not yet in-service because of material delays for initial network antenna installations. Plan to complete goal in Q4. |  | N/A |  |  |  |  | Behind Plan, Likely to Meet Year-end Goal | Plan to complete goal in Q4. | [6 empty] | No
SCE | 2021-11-02 | Situational Awareness & Forecasting | 7.3.2 | Fault indicators for detecting faults on electric lines and equipment |  | 3 | N/A | N/A | SCE_Situational Awareness & Forecasting_Fault indicators for detecting faults on electric lines and equipment _N/A_2021 | 200 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Situational Awareness & Forecasting | 7.3.2 | Forecast of a fire risk index, fire potential index, or similar |  | 4 | Fire Potential Index | SA-2 | SCE_Situational Awareness & Forecasting_Forecast of a fire risk index, fire potential index, or similar _SA-2_2021 | 201 | N/A | N/A | [8 empty] | 1) Backcast 20 years of FPI using FPI 2.0 before typical height of fire season (Q3) to determine historical performance compared to current FPI 2) Run FPI 2.0 in parallel with the current FPI and compare outputs for the 2021 fire season | Continuing to evaluate fuel and weather equation options. SCE is currently testing the usefulness of applying relative fuel moisture values instead of absolute values in Fire Potential Index (FPI) 2.0 fuel equations to inform circuit level decision making. | Currently evaluating FPI 2.0 data output calculated on the circuit level and backcasted over a 40-year historical period by Fire Climate Zone. | SCE is improving the accuracy of its FPI (referred to as FPI 2.0) through the integration of historical weather and vegetation data for more precise PSPS decision-making. Team experienced a delay in finalizing the circuit-level FPI 2.0 output, which resulted in delayed documentation of the FPI 2.0 methodology. Documentation of this methodology is now expected to be completed by early Q4. |  | Behind Plan, Likely to Meet Year-end Goal | Documentation of the FPI 2.0 methodology began in September to stay on pace for a November completion | [6 empty] | No
SCE | 2021-11-02 | Situational Awareness & Forecasting | 7.3.2 | Forecast of a fire risk index, fire potential index, or similar |  | 4 | Fuel Sampling Program | SA-5 | SCE_Situational Awareness & Forecasting_Forecast of a fire risk index, fire potential index, or similar _SA-5_2021 | 203 | N/A | N/A | [8 empty] | Maintain periodic fuel sampling across SCE’s HFRA and evaluate the need to sample additional locations | Vendor continues to fill gaps in local fire agencies’ fuel sampling programs by supplying reports with quality data in a timely fashion, per project plan. | Vendor continues to fill gaps in local fire agencies’ fuel sampling programs by supplying reports with quality data in a timely fashion, per project plan. | Vendor continues to supply reports every 2 weeks per project plan. Plan to review and assess the fuel sampling output in Q4. |  | On Track | [7 empty] | No
SCE | 2021-11-02 | Situational Awareness & Forecasting | 7.3.2 | Forecast of a fire risk index, fire potential index, or similar |  | 4 | Remote Sensing / Satellite Fuel Moisture | SA-7 | SCE_Situational Awareness & Forecasting_Forecast of a fire risk index, fire potential index, or similar _SA-7_2021 | 204 | N/A | N/A | [8 empty] | Initiate wind profiler pilot project to validate weather model performance for potential improvements to weather models | SCE to issue PO to vendor by Q2 | Working with vendor to identify anticipated scope of work for vegetation modeling tools. | Plan to collect wind profiler data in Q4 to analyze output. Completed onboarding with vendor to begin Satellite Fuel Moisture work in Q4 to potentially improve weather models. |  | On Track | [7 empty] | No
SCE | 2021-11-02 | Situational Awareness & Forecasting | 7.3.2 | Forecast of a fire risk index, fire potential index, or similar |  | 4 | Fire Science Enhancements | SA-8 | SCE_Situational Awareness & Forecasting_Forecast of a fire risk index, fire potential index, or similar _SA-8_2021 | 205 | N/A | N/A | [8 empty] | Evaluate current wildfire events in context of 40-year history of wildfires | SCE plans to develop and operationalize climatology products in Q3 and Q4. In Q1-Q3 SCE is working with vendor to initiate contract and develop output of historical weather data. Issuance of contract was slightly behind plan at the end of Q1 | SCE plans to develop and operationalize climatology products in Q3 and Q4. In Q1-Q3 SCE is working with vendor to initiate contract and develop output of historical weather data. | While the historical climatological data output is likely to be produced and reviewed in 2021, the development of climatological products will not be completed this year as vendor work was reprioritized to support initiatives that will inform PSPS decision making in 2021. While this activity is at risk for not meeting its year end target, it is not intended to directly mitigate wildfire risk in 2021. |  | Behind Plan, At-Risk of Not Meeting Year-end Goal | Will continue to work with vendor in Q4 2021 and 2022 to make progress in producing climatological data output and evaluating quality | [6 empty] | No
SCE | 2021-11-02 | Situational Awareness & Forecasting | 7.3.2 | Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions |  | 5 | N/A | N/A | SCE_Situational Awareness & Forecasting_Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions _N/A_2021 | 206 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Situational Awareness & Forecasting | 7.3.2 | Weather forecasting and estimating impacts on electric lines and equipment |  | 6 | Weather and Fuels Modeling System | SA-3 | SCE_Situational Awareness & Forecasting_Weather forecasting and estimating impacts on electric lines and equipment _SA-3_2021 | 207 | N/A | N/A | [8 empty] | Install two additional High-Performance Computing Clusters (HPCCs) to facilitate the installation and Operationalization of the Next Generation Weather Modeling System allowing or more precise, higher resolution output | Components are arriving and High-Performance Computing Clusters (HPCCs) are in process of being built. These new HPCCs will enhance weather/fuel condition data available for PSPS decision making by increasing data resolution, decreasing computing times, and extending forecast horizons further into the future. The location of new HPCCs will be the Irvine Datacenter. | Building of the HPCCs completed in Q2 and beginning point testing to identify faulty components. | HPCCs were built in Q2. In Q3, SCE performed additional testing through the year before operationalizing the HPCCs and plan to begin producing higher resolution output from both HPCCs in Q4. |  | On Track | [7 empty] | No
SCE | 2021-11-02 | Situational Awareness & Forecasting | 7.3.2 | Weather forecasting and estimating impacts on electric lines and equipment |  | 6 | Fire Spread Modeling | SA-4 | SCE_Situational Awareness & Forecasting_Weather forecasting and estimating impacts on electric lines and equipment _SA-4_2021 | 209 | N/A | N/A | [8 empty] | Develop a methodology and a strategy to test FireCast/FireSim implementation into PSPS decision making based on backcast information by Q3 | Successfully transferred 4.5 million FPI records from 2020 and circuit geometries to vendor to serve as basis for future analyses. | Spread Modeling has fallen behind due to vendor delays on the PSPS decision making analysis. Plan to review data with vendor in mid-July and discuss next steps. | Completed development of methodology for incorporating risk and consequence data. |  | Completed | [7 empty] | No
SCE | 2021-11-02 | Grid Design & System Hardening | 7.3.3 | Capacitor maintenance and replacement program |  | 1 | N/A | N/A | SCE_Grid Design & System Hardening_Capacitor maintenance and replacement program _N/A_2021 | 212 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Grid Design & System Hardening | 7.3.3 | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault |  | 2 | Circuit Breaker Relay Hardware for Fast Curve | SH-6 | SCE_Grid Design & System Hardening_Circuit breaker maintenance and installation to de-energize lines upon detecting a fault _SH-6_2021 | 213 | # of installations and place into service | Replace/upgrade 60 relay units in HFRA. SCE will strive to replace/upgrade 86 relay units in HFRA, subject to resource constraints and other execution risks | Replace/Upgrade 7 relays | Replace/Upgrade 27 relays | Replace/Upgrade 45 relays | Goal has been met and SCE will continue to work towards the strive target | Installed/replaced 15 CB Replays in Q1 | Installed/replaced 25 CB Replays through Q2. | Installed/replaced 64 CB Replays through Q3. |  | N/A |  |  |  |  | Completed | [7 empty] | No
SCE | 2021-11-02 | Grid Design & System Hardening | 7.3.3 | Covered conductor installation |  | 3 | Covered Conductor | SH-1 | SCE_Grid Design & System Hardening_Covered conductor installation _SH-1_2021 | 214 | # of circuit miles in HFRA | SCE expects to install 1,000 circuit miles of covered conductor in SCE’s HFRA but will attempt to install as many as 1,400 circuit miles of covered conductor in SCE’s HFRA, subject to resources constraints and other execution risks | Install 260 miles | Install 545 miles | Install 790 miles | goal has been met and SCE will continue to work towards the strive target | 270 circuit miles installed | ~540 circuiit miles installed. Once a final GRC decision is issued, SCE will reevaluate its covered conductor strategy and scope along with alternative strategies as appropriate to protect public safety. | ~1000 miles installed |  | N/A |  |  |  |  | Completed | [7 empty] | No
SCE | 2021-11-02 | Grid Design & System Hardening | 7.3.3 | Covered conductor installation |  | 3 | Tree Attachment Remediation | SH-10 | SCE_Grid Design & System Hardening_Covered conductor installation _SH-10_2021 | 217 | # of tree attachment remediations | Remediate 500 tree attachments. SCE will strive to complete over 600 tree attachment remediations, subject to resource constraints and other execution risks | Remediate 90 Tree Attachments | Remediate 240 Tree Attachments | Remediate 430 Tree Attachments | Remediate 500 Tree Attachments | 92 completions to date. | 89 completions to date | ~420 completions to date |  | N/A |  |  |  |  | Behind Plan, Likely to Meet Year-end Goal | Scope has been released to regions and plan to meet year end goal | [6 empty] | No
SCE | 2021-11-02 | Grid Design & System Hardening | 7.3.3 | Covered conductor maintenance |  | 4 | N/A | N/A | SCE_Grid Design & System Hardening_Covered conductor maintenance _N/A_2021 | 219 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Grid Design & System Hardening | 7.3.3 | Crossarm maintenance, repair, and replacement |  | 5 | N/A | N/A | SCE_Grid Design & System Hardening_Crossarm maintenance, repair, and replacement _N/A_2021 | 219 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Grid Design & System Hardening | 7.3.3 | Distribution pole replacement and reinforcement, including with composite poles |  | 6 | N/A | N/A | SCE_Grid Design & System Hardening_Distribution pole replacement and reinforcement, including with composite poles _N/A_2021 | 219 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Grid Design & System Hardening | 7.3.3 | Expulsion fuse replacement |  | 7 | Branch Line Protection Strategy | SH-4 | SCE_Grid Design & System Hardening_Expulsion fuse replacement _SH-4_2021 | 219 | # of locations with installed / replaced fuses | Install or replace fusing at 330 fuse installation Locations SCE will strive to install or replace fusing at 421 locations, subject to resource constraints and other execution risks | 0 installations. Installations to commence end of Q3. | 20 installations. Installations to commence end of Q3. | 180 installations. Installations to commence end of Q3. | Install or replace fusing at 330 fuse installation Locations | Engineering and design work to continue through Q2 and installations to begin in Q3. | ~140 installed or replaced | ~340 installed or replaced |  | N/A |  |  |  |  | Completed | [7 empty] | No
SCE | 2021-11-02 | Grid Design & System Hardening | 7.3.3 | Grid topology improvements to mitigate or reduce PSPS events |  | 8 | PSPS-Driven Grid Hardening Work | SH-7 | SCE_Grid Design & System Hardening_Grid topology improvements to mitigate or reduce PSPS events _SH-7_2021 | 221 | N/A | N/A | [8 empty] | SCE will develop a methodology to project probability of PSPS de-energization and impact. Utilizing this methodology, SCE will adopt a more targeted approach by evaluating highly impacted circuits from the remaining 50% circuits in HFRA | Documentation of methodology is under development and on track for the 2021 evaluation. Identification of the remaining 50% of riskiest circuits will follow in Q2. | Documentation of methodology is under development and on track for the 2021 evaluation. Identification of the riskiest circuits within the remaining 50% of unevaluated circuits was completed by June as planned. | Review of the second 50% of riskiest circuits is under development and expected to complete in Q4. |  | On Track | [7 empty] | No
SCE | 2021-11-02 | Grid Design & System Hardening | 7.3.3 | Grid topology improvements to mitigate or reduce PSPS events |  | 8 | Microgrid Assessment | SH-12 | SCE_Grid Design & System Hardening_Grid topology improvements to mitigate or reduce PSPS events _SH-12_2021 | 222 | N/A | N/A | [8 empty] | Perform internal assessment of vendor bid and location options. If assessment favorable, issue engineering procurement construction (EPC) contract | Undergoing vendor evaluation. | Undergoing vendor evaluation. | Site owner's August vote was not in favor of proceeding with signing a contract for land lease. SCE has explored alternative customers but has been unsuccesful in securing alternative customer sites. |  | Behind Plan, Likely to Meet Year-end Goal | Site owner is expected to re-engage and revisit land lease contract in Q4. | [6 empty] | No
SCE | 2021-11-02 | Grid Design & System Hardening | 7.3.3 | Installation of system automation equipment |  | 9 | Installation of System Automation Equipment - RAR / RCS | SH-5 | SCE_Grid Design & System Hardening_Installation of system automation equipment _SH-5_2021 | 223 | # of RARs / RCSs installed and operationalized | N/A – If RARs/RCSs are determined to be necessary based on the SH-7 analysis, SCE will develop appropriate project plans | N/A – If RARs/RCSs are determined to be necessary based on the SH-7 analysis, SCE will develop appropriate project plans | N/A – If RARs/RCSs are determined to be necessary based on the SH-7 analysis, SCE will develop appropriate project plans |  |  | Awaiting SH-7 analysis results to determine necessity—analysis is estimated to conclude by the early Q2. | Awaiting SH-7 analysis results to determine necessity—analysis is estimated to conclude in Q3. | Activity met goal in Q3 in accordance with Corrective Action Plan. Total of 17 automatic devices and 8 isolation devices installed. |  | N/A |  |  |  |  | Completed | [7 empty] | No
SCE | 2021-11-02 | Grid Design & System Hardening | 7.3.3 | Maintenance, repair, and replacement of connectors, including hotline clamps |  | 10 | N/A | N/A | SCE_Grid Design & System Hardening_Maintenance, repair, and replacement of connectors, including hotline clamps _N/A_2021 | 225 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Grid Design & System Hardening | 7.3.3 | Mitigation of impact on customers and other residents affected during PSPS event |  | 11 | N/A | N/A | SCE_Grid Design & System Hardening_Mitigation of impact on customers and other residents affected during PSPS event _N/A_2021 | 225 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Grid Design & System Hardening | 7.3.3 | Other corrective action |  | 12 | Long Span Initiative | SH-14 | SCE_Grid Design & System Hardening_Other corrective action _SH-14_2021 | 226 | # of assessments | Complete all field assessments for locations and Corresponding remediations. Remediate the highest risk locations, estimating that 300, and up to 600, locations will be remediated in 2021, subject to the completion timeline for inspections, resource constraints and other execution risks | 0 assessments | 75 assessments through Q2 | 225 assessments through Q3 | 300 assessments through 2021 | As of Q1 2021, 58 spans of the identified 300 high-risk locations have been remediated to date. Upon further validation of 2020 data, SCE notes that some locations were remediated in 2020. SCE clarifies that it will remediate the 300-600 highest risk locations by 2021, subject to the completion timeline for inspections, resource constraints and other execution risks. | ~170 assessments | ~160 spans of available scope have been remediated to date in the manner described in the WMP. SCE clarifies that it will remediate the 300-600 locations in 2021, subject to completion timeline , resource constraints and other execution risks. Additional scope is being released for completion. |  | N/A |  |  |  |  | Behind Plan, Likely to Meet Year-end Goal | Additional scope is being released for completion. | [6 empty] | No
SCE | 2021-11-02 | Grid Design & System Hardening | 7.3.3 | Pole loading infrastructure hardening and replacement program based on pole loading assessment program |  | 13 | N/A | N/A | SCE_Grid Design & System Hardening_Pole loading infrastructure hardening and replacement program based on pole loading assessment program _N/A_2021 | 227 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Grid Design & System Hardening | 7.3.3 | Transformers maintenance and replacement |  | 14 | N/A | N/A | SCE_Grid Design & System Hardening_Transformers maintenance and replacement _N/A_2021 | 227 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Grid Design & System Hardening | 7.3.3 | Transmission tower maintenance and replacement |  | 15 | C-Hooks | SH-13 | SCE_Grid Design & System Hardening_Transmission tower maintenance and replacement _SH-13_2021 | 227 | # of C-hooks | Replace C-Hooks on at least 40 structures in HFRA. SCE will strive to replace all Chooks in HFRA, currently estimated between 50- 60 structures | 0 replacements. Sites and locations to be finalized in Q1. | 0 replacements. Installations to begin in Q4 | 16 replacements | 50 replacements | Sites and locations finalized. Environmental screenings in progress. Engineering design to be completed in Q2 and installations to begin in Q4. | procured all material, issued all design drawings, finalized environmental requirements, and assembled big packages in Q2. | Sites and locations finalized. Environmental screenings and engineering design completed. Replaced C-Hooks on 16 structures in Q3. |  | N/A |  |  |  |  | On Track | [7 empty] | No
SCE | 2021-11-02 | Grid Design & System Hardening | 7.3.3 | Undergrounding of electric lines and/or equipment |  | 16 | Undergrounding Overhead Conductor | SH-2 | SCE_Grid Design & System Hardening_Undergrounding of electric lines and/or equipment _SH-2_2021 | 228 | # of circuit miles in HFRA | Install 4 miles of undergrounded HFRA circuits SCE will attempt to install 6 miles of undergrounded HFRA circuits, subject to resource constraints and other execution risks, such as permitting, environmental or coordinating with other utilities. | 0 circuit miles underground in Q1. Assessments for construction to be completed in Q1. | 0 circuit miles underground in Q1. Construction to begin in late Q3 | 0 circuit miles underground in Q1. Construction to begin in late Q3 | 4 circuit miles in HFRA | Construction to begin in Q2. First miles to be completed in Q3. | Construction to begin in Q2. First miles to be completed in Q3. | Construction began in Q2. At least 4 miles are on-track for year-end completion |  | N/A |  |  |  |  | Behind Plan, Likely to Meet Year-end Goal | At least 4 miles are on-track for year-end completion | [6 empty] | Yes | In Review
SCE | 2021-11-02 | Grid Design & System Hardening | 7.3.3 | Updates to grid topology to minimize risk of ignition in HFTDs |  | 17 | Transmission Open Phase Detection | SH-8 | SCE_Grid Design & System Hardening_Updates to grid topology to minimize risk of ignition in HFTDs _SH-8_2021 | 230 | # of installations on transmission circuits | Install transmission open phase detection devices on 10 transmission circuits | 0 installations. Finish evaluation of 220kv transmission lines and finalize project locations. | 0 installations. Finish evaluation of 220kv transmission lines and finalize project locations. | 8 installations | 10 transmission circuits | Protection review completed for 5 of 10 lines with installations to begin in early Q3. | Protection review completed for 5 of 10 lines with installations to begin in early Q3. | Installation has been completed on 6 circuits |  | N/A |  |  |  |  | Behind Plan, Likely to Meet Year-end Goal | All preparations are underway for additional device installation scheduled for Q4 | [6 empty] | No
SCE | 2021-11-02 | Grid Design & System Hardening | 7.3.3 | Updates to grid topology to minimize risk of ignition in HFTDs | Legacy Facilities | 17 | Legacy Facilities | SH-11 | SCE_Grid Design & System Hardening_Updates to grid topology to minimize risk of ignition in HFTDs _SH-11_2021 | 231 | N/A | N/A | [8 empty] | Perform evaluation on 5 circuits for possible hardening. Create 2 project plans based on 2020 engineering assessments on low voltage site. Complete 12 additional assessments on grounding studies/lighting arrestor. | In Q1 SCE evaluated 2 circuits in Big Creek and completed grounding studies/lighting assessments on 4 sites. Assessments of low voltage sites to begin in Q2. | SCE evaluated 2 circuits in Big Creek and completed grounding studies/lighting assessments on 8 sites. Assessments of low voltage sites were completed in Q2. | Completed milestone of assessing five circuits in 2021 and completed grounding studies/lighting assessments on 12 sites. Plan to complete grounding and lightning arrestor studies by Q4. Assessments of low voltage sites were completed in Q2. |  | On Track | [7 empty] | No
SCE | 2021-11-02 | Grid Design & System Hardening | 7.3.3 | Updates to grid topology to minimize risk of ignition in HFTDs |  | 17 | Vertical Switches | SH-15 | SCE_Grid Design & System Hardening_Updates to grid topology to minimize risk of ignition in HFTDs _SH-15_2021 | 232 | # of switches | Install 20 switches in HFRA. SCE will strive to install 30 switches in HFRA | 0 installations. Preparation work for Q3 ramp up. | 0 installations. Preparation work for Q3 ramp up. | 10 installations | 20 installations | In Q1 SCE evaluated scope. In Q2 SCE will be working on engineering design and installations to begin in Q3. | 2 installations | 3 installations |  | N/A |  |  |  |  | Behind Plan, Likely to Meet Year-end Goal | All released switches are on track for year-end completion | [6 empty] | No
SCE | 2021-11-02 | Asset Management & Inspections | 7.3.4 | Detailed inspections of distribution electric lines and equipment |  | 1 | N/A | N/A | SCE_Asset Management & Inspections_Detailed inspections of distribution electric lines and equipment _N/A_2021 | 234 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Asset Management & Inspections | 7.3.4 | Detailed inspections of transmission electric lines and equipment |  | 2 | N/A | N/A | SCE_Asset Management & Inspections_Detailed inspections of transmission electric lines and equipment _N/A_2021 | 235 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Asset Management & Inspections | 7.3.4 | Improvement of inspections |  | 3 | Inspection Work Management Tools | IN-8 | SCE_Asset Management & Inspections_Improvement of inspections _IN-8_2021 | 236 | N/A | N/A | [8 empty] | Transition Aerial and Transmission ground inspection process to a single digital platform with at least 75% of inspectors trained to use the tool by year end 2021. Deploy scope mapping tool with GIS visualization to Distribution | Implemented a mobile inspection application update for Distribution ground inspections and completed work to utilize Artificial Intelligence/Machine Learning quality models within existing processes. | Behind plan due to technical challenges which have caused significant delays with development of the Transmission Ground Inspection application. The complexity and uncertainty of the technical issues cause the goal to be at-risk for year end. The Distribution and Transmission Aerial applications are on track for year end. | Behind plan due to technical challenges which have caused significant delays with development of the Transmission Ground Inspection application. The training portion of the goal will not be completed in 2021 due to the technical challenges. The Distribution and Transmission Aerial applications are on track for year end. |  | Behind Plan, At-Risk of Not Meeting Year-end Goal | The training portion of the goal will not be completed in 2021 due to the technical challenges. The Distribution and Transmission Aerial applications are on track for year end. | [6 empty] | No
SCE | 2021-11-02 | Asset Management & Inspections | 7.3.4 | Infrared inspections of distribution electric lines and equipment |  | 4 | Infrared Inspection of Energized Overhead Distribution Facilities and Equipment | IN-3 | SCE_Asset Management & Inspections_Infrared inspections of distribution electric lines and equipment _IN-3_2021 | 238 | % of distribution circuit miles in HFRA | Inspect approximately 50% of distribution circuits in HFRA. | Complete inspections on ~24% of distribution circuits in HFRA, approximately 2,160 inspections. | Completed inspections on ~50% of distribution circuits in HFRA, approximately 4,400 inspections. | Completed inspections on ~50% of distribution circuits in HFRA, approximately 4,400 inspections. | Completed inspections on ~50% of distribution circuits in HFRA, approximately 4,400 inspections. | Completed inspections on ~29% of distribution circuits in HFRA, approximately 2,600 inspections. | Completed inspections on ~50% of distribution circuits in HFRA, approximately 4,400 inspections. | Completed inspections on ~50% of distribution circuits in HFRA, approximately 4,400 inspections. |  | N/A |  |  |  |  | Completed | [7 empty] | No
SCE | 2021-11-02 | Asset Management & Inspections | 7.3.4 | Infrared inspections of transmission electric lines and equipment |  | 5 | Infrared Inspection, Corona Scanning, and High-Definition Imagery of Energized Overhead Transmission facilitites and Equipment | IN-4 | SCE_Asset Management & Inspections_Infrared inspections of transmission electric lines and equipment _IN-4_2021 | 239 | # of transmission circuit miles in HFRA | Inspect 1,000 transmission circuit miles on HFRA circuits | 0 circuit miles inspected. Preparation work for Q2 ramp up. | 500 circuit miles planned. Expect ramp up in Q3 | 500 circuit miles planned. Began ramp up in Q3 and will push into Q4 | 1,000 circuit miles planned | Inspection scope development has been completed, planning for flight plans is ongoing and first inspections to occur in Q2. | 73 circuit miles inspected. Plan ramp up in Q3 | Resumed inspections in Q3 after delays due to malfunctioning camera equipment and travel restrictions impeding equipment repair. ~450 circuit miles completed through Q3 and plan complete goal in Q4. |  | N/A |  |  |  |  | On Track | [7 empty] | No
SCE | 2021-11-02 | Asset Management & Inspections | 7.3.4 | Intrusive pole inspections |  | 6 | N/A | N/A | SCE_Asset Management & Inspections_Intrusive pole inspections _N/A_2021 | 241 | N/A | [9 empty] | N/A
SCE | 2021-11-02 | Asset Management & Inspections | 7.3.4 | LiDAR inspections of distribution electric lines and equipment |  | 7 | N/A | N/A | SCE_Asset Management & Inspections_LiDAR inspections of distribution electric lines and equipment _N/A_2021 | 242 | N/A | [9 empty] | N/A
SCE | 2021-11-02 | Asset Management & Inspections | 7.3.4 | LiDAR inspections of transmission electric lines and equipment |  | 8 | N/A | N/A | SCE_Asset Management & Inspections_LiDAR inspections of transmission electric lines and equipment _N/A_2021 | 242 | N/A | [9 empty] | N/A
SCE | 2021-11-02 | Asset Management & Inspections | 7.3.4 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations |  | 9 | Distribution High Fire Risk Informed Inspections in HFRA | IN-1.1 | SCE_Asset Management & Inspections_Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations _IN-1.1_2021 | 242 | # of structures in HFRA | Inspect between 163,000 and 198,000 structures in HFRA, via both ground and aerial inspections | Inspect 97,998 ground Structures. Inspect 5,753 aerial structures | Inspect 163,000 ground structures. Inspect 117,924 aerial structures | Inspect 163,000 ground structures. Inspect 163,000 aerial structures | Goal met for ground and aerial inspections in Q3 and SCE will continue to work towards the strive target | Completed 108,000 ground inspections and 6,300 aerial inspections. Aerial inspections to begin ramp up in Q2. | Completed ~173,200 ground inspections and ~105,700 aerial inspections. | Completed ~185,000 ground inspections and ~178,000 aerial inspections. |  | N/A |  |  |  |  | Completed | [7 empty] | Yes | In Review
SCE | 2021-11-02 | Asset Management & Inspections | 7.3.4 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations |  | 9 | Generation High Fire Risk Informed Inspections in HFRA | IN-5 | SCE_Asset Management & Inspections_Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations _IN-5_2021 | 246 | # of structures in HFRA | Complete inspection of 181 generation-related assets in HFRA | 0 inspections. Preparation work for Q2 ramp up. | 85 planned through Q2 | 181 Planned through Q3 | ~230 inspections | Preparation work for 2021 inspections conducted in Q1. Generation inspections to begin in Q2. | ~100 inspections | Completed ~230 Generation inspections and will continue in Q3. |  | N/A |  |  |  |  | Completed | [7 empty] | No
SCE | 2021-11-02 | Asset Management & Inspections | 7.3.4 | Other discretionary inspection of transmission electric lines and equipment, beyond inspections mandated by rules and regulations |  | 10 | Transmission High Fire Risk Informed Inspections in HFRA | IN-1.2 | SCE_Asset Management & Inspections_Other discretionary inspection of transmission electric lines and equipment, beyond inspections mandated by rules and regulations_IN-1.2_2021 | 248 | # of structures in HFRA | Inspect between 16,800 and 22,800 structures in HFRA, via both ground and aerial inspections. | Inspect 4,730 ground structures. Inspect 2,520 aerial structures | Inspect 16,800 ground structures. Inspect 15,120 aerial structures | Inspect 16,800 ground structures. Inspect 16,800 aerial structures | Goal met for ground and aerial inspections in Q3 and SCE will continue to work towards the strive target | Completed 4,800 ground inspections and 4,600 aerial inspections. | Completed ~17,000 ground inspections and ~17,300 aerial inspections. | Completed ~21,100 ground and ~20,600 aerial inspections. |  | N/A |  |  |  |  | Completed | [7 empty] | Yes | In Review
SCE | 2021-11-02 | Asset Management & Inspections | 7.3.4 | Patrol inspections of distribution electric lines and equipment |  | 11 | N/A | N/A | SCE_Asset Management & Inspections_Patrol inspections of distribution electric lines and equipment _N/A_2021 | 252 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Asset Management & Inspections | 7.3.4 | Patrol inspections of transmission electric lines and equipment |  | 12 | N/A | N/A | SCE_Asset Management & Inspections_Patrol inspections of transmission electric lines and equipment _N/A_2021 | 253 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Asset Management & Inspections | 7.3.4 | Pole loading assessment program to determine safety factor |  | 13 | N/A | N/A | SCE_Asset Management & Inspections_Pole loading assessment program to determine safety factor _N/A_2021 | 253 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Asset Management & Inspections | 7.3.4 | Quality assurance / quality control of inspections |  | 14 | N/A | N/A | SCE_Asset Management & Inspections_Quality assurance / quality control of inspections _N/A_2021 | 255 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Asset Management & Inspections | 7.3.4 | Substation inspections |  | 15 | N/A | N/A | SCE_Asset Management & Inspections_Substation inspections _N/A_2021 | 256 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Vegetation Management & Inspections | 7.3.5 | Additional efforts to manage community and environmental impacts |  | 1 | N/A | N/A | SCE_Vegetation Management & Inspections_Additional efforts to manage community and environmental impacts _N/A_2021 | 258 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Vegetation Management & Inspections | 7.3.5 | Detailed inspections of vegetation around distribution electric lines and equipment |  | 2 | N/A | N/A | SCE_Vegetation Management & Inspections_Detailed inspections of vegetation around distribution electric lines and equipment _N/A_2021 | 261 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Vegetation Management & Inspections | 7.3.5 | Detailed inspections of vegetation around transmission electric lines and equipment |  | 3 | N/A | N/A | SCE_Vegetation Management & Inspections_Detailed inspections of vegetation around transmission electric lines and equipment _N/A_2021 | 262 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Vegetation Management & Inspections | 7.3.5 | Emergency response vegetation management due to red flag warning or other urgent conditions |  | 4 | N/A | N/A | SCE_Vegetation Management & Inspections_Emergency response vegetation management due to red flag warning or other urgent conditions _N/A_2021 | 262 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Vegetation Management & Inspections | 7.3.5 | Fuel management and reduction of “slash” from vegetation management activities |  | 5 | Expanded Pole Brushing | VM-2 | SCE_Vegetation Management & Inspections_Fuel management and reduction of “slash” from vegetation management activities _VM-2_2021 | 265 | # of poles cleared | SCE plans to pole brush between 200,000 and 300,000 Distribution poles | 31000 | 91200 | 157600 | 200000 | Cleared ~34,400 poles. Productivity is expected to increase throughout Q2 as crews gain experience with new digital work tools. | Cleared ~74,200 poles | Cleared ~112,200 poles |  | N/A |  |  |  |  | Behind Plan,At-risk of Not Meeting Year-end Goal | Additional contractor crews onboarded and started work in October with continued ramp up expectations addressed to meet goal | [6 empty] | No
SCE | 2021-11-02 | Vegetation Management & Inspections | 7.3.5 | Fuel management and reduction of “slash” from vegetation management activities |  | 5 | Expanded Clearances for Legacy Facilities | VM-3 | SCE_Vegetation Management & Inspections_Fuel management and reduction of “slash” from vegetation management activities _VM-3_2021 | 266 | # of sites treated | Treat 46 sites | 0 sites treated. Preparation work for Q2 ramp up. | 23 sites | 46 sites | 46 sites | 11 sites treated | 34 sites | 47 sites |  | N/A |  |  |  |  | Completed | [7 empty] | No
SCE | 2021-11-02 | Vegetation Management & Inspections | 7.3.5 | Improvement of inspections |  | 6 | N/A | N/A | SCE_Vegetation Management & Inspections_Improvement of inspections _N/A_2021 | 267 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Vegetation Management & Inspections | 7.3.5 | LiDAR inspections of vegetation around distribution electric lines and equipment |  | 7 | N/A | N/A | SCE_Vegetation Management & Inspections_LiDAR inspections of vegetation around distribution electric lines and equipment _N/A_2021 | 268 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Vegetation Management & Inspections | 7.3.5 | LiDAR inspections of vegetation around transmission electric lines and equipment |  | 8 | N/A | N/A | SCE_Vegetation Management & Inspections_LiDAR inspections of vegetation around transmission electric lines and equipment _N/A_2021 | 270 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Vegetation Management & Inspections | 7.3.5 | Other discretionary inspection of vegetation around distribution electric lines and equipment, beyond inspections mandated by rules and regulations |  | 9 | N/A | N/A | SCE_Vegetation Management & Inspections_Other discretionary inspection of vegetation around distribution electric lines and equipment, beyond inspections mandated by rules and regulations_N/A_2021 | 271 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Vegetation Management & Inspections | 7.3.5 | Other discretionary inspection of vegetation around transmission electric lines and equipment, beyond inspections mandated by rules and regulations |  | 10 | N/A | N/A | SCE_Vegetation Management & Inspections_Other discretionary inspection of vegetation around transmission electric lines and equipment, beyond inspections mandated by rules and regulations_N/A_2021 | 271 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Vegetation Management & Inspections | 7.3.5 | Patrol inspections of vegetation around distribution electric lines and equipment |  | 11 | N/A | N/A | SCE_Vegetation Management & Inspections_Patrol inspections of vegetation around distribution electric lines and equipment_N/A_2021 | 271 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Vegetation Management & Inspections | 7.3.5 | Patrol inspections of vegetation around transmission electric lines and equipment |  | 12 | N/A | N/A | SCE_Vegetation Management & Inspections_Patrol inspections of vegetation around transmission electric lines and equipment_N/A_2021 | 273 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Vegetation Management & Inspections | 7.3.5 | Quality assurance / quality control of inspections |  | 13 | N/A | N/A | SCE_Vegetation Management & Inspections_Quality assurance / quality control of inspections_N/A_2021 | 273 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Vegetation Management & Inspections | 7.3.5 | Recruiting and training of vegetation management personnel |  | 14 | N/A | N/A | SCE_Vegetation Management & Inspections_Recruiting and training of vegetation management personnel_N/A_2021 | 274 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Vegetation Management & Inspections | 7.3.5 | Remediation of at-risk species |  | 15 | N/A | N/A | SCE_Vegetation Management & Inspections_Remediation of at-risk species_N/A_2021 | 276 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Vegetation Management & Inspections | 7.3.5 | Removal and remediation of trees with strike potential to electric lines and equipment |  | 16 | Hazard Tree Management Program | VM-1 | SCE_Vegetation Management & Inspections_Removal and remediation of trees with strike potential to electric lines and equipment _VM-1_2021 | 278 | # of trees assessed | Assess between 150,000 and 200,000 trees for hazardous conditions and perform prescribed mitigation in accordance with program guidelines and schedules | 11956 | 58756 | 106956 | 150000 | ~12,600 trees have been assessed in Q1 and prescribed mitigations are on track in accordance with program guidelines and schedules. The number of assessors is being ramped up throughout Q1 and Q2. | ~64,900 trees have been assessed through Q2 and prescribed mitigations are on track in accordance with program guidelines and schedules. | ~108,800 trees have been assessed through Q3 and prescribed mitigations are on track in accordance with program guidelines and schedules. |  | N/A |  |  |  |  | On Track | [7 empty] | Yes | In Review
SCE | 2021-11-02 | Vegetation Management & Inspections | 7.3.5 | Removal and remediation of trees with strike potential to electric lines and equipment |  | 16 | Dead and Dying Tree Removal | VM-4 | SCE_Vegetation Management & Inspections_Removal and remediation of trees with strike potential to electric lines and equipment _VM-4_2021 | 280 | N/A | N/A | [8 empty] | Perform Drought Relief Initiative (DRI) annual inspections and perform prescribed mitigations in accordance with program guidelines and schedules. | On track to complete first pass inspections in Q2. Subsequent inspection passes will be completed throughout the rest of 2021. Prescribed mitigations are on track in accordance with program guidelines and schedules | Began first pass inspections in Q2. Subsequent inspection passes will be completed throughout the rest of 2021. Prescribed mitigations are on track in accordance with program guidelines and schedules | On track to complete the first and second circuit passes as planned. ~1050 assessments completed through Q2. Continuing to monitor contractor resource plans to ensure timely completions. |  | On Track | [7 empty] | Yes | In Review
SCE | 2021-11-02 | Vegetation Management & Inspections | 7.3.5 | Substation inspections |  | 17 | N/A | N/A | SCE_Vegetation Management & Inspections_Substation inspections_N/A_2021 | 281 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Vegetation Management & Inspections | 7.3.5 | Substation vegetation management |  | 18 | N/A | N/A | SCE_Vegetation Management & Inspections_Substation vegetation management _N/A_2021 | 281 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Vegetation Management & Inspections | 7.3.5 | Vegetation inventory system |  | 19 | VM Work Management Tool | VM-6 | SCE_Vegetation Management & Inspections_Vegetation inventory system _VM-6_2021 | 282 | N/A | N/A | [8 empty] | Continue Work Management Tool (Arbora) agile development and releases in accordance with project plan – complete full rollout of Dead & Dying Tree Removal and Hazard Tree Mitigation, and conduct discovery and design architecture associated with Line Clearing | Completed initial discovery and design architecture for the Hazard Tree Management Program and Dead and Dying Tree Removal. Expecting pilot to launch in Q2 with full rollout planned for Q4. | Completed initial discovery and design architecture for the Hazard Tree Management Program and Dead and Dying Tree Removal. Pilot delayed until Q3 due to IT issues, however, a full rollout planned for Q4. | Completed initial discovery and design architecture for the routine Line Clearing portion of this activity and deployed as planned. However, The Hazard Tree Management Program and Dead and Dying Tree Removal has had to re-design architecture due to data volume limitations and inability to calculate and assess risk scores, requiring additional development time and moving timeline to 2022. |  | Behind Plan,At-risk of Not Meeting Year-end Goal | Due to development delays by SCE technical partners, there is no current opportunity to shorten our development timeline to meet our VM-6 WMP goal. With that said, adjusted timeline does currently allow SCE to stay on-track for “Line Clearing” (Routine) deployment timeline. | [6 empty] | No
SCE | 2021-11-02 | Vegetation Management & Inspections | 7.3.5 | Vegetation management to achieve clearances around electric lines and equipment |  | 20 | N/A | N/A | SCE_Vegetation Management & Inspections_Vegetation management to achieve clearances around electric lines and equipment _N/A_2021 | 283 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Grid Operations & Operating Protocols | 7.3.6 | Automatic recloser operations |  | 1 | N/A | N/A | SCE_Grid Operations & Operating Protocols_Automatic recloser operations _N/A_2021 | 287 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Grid Operations & Operating Protocols | 7.3.6 | Crew-accompanying ignition prevention and suppression resources and services |  | 2 | N/A | N/A | SCE_Grid Operations & Operating Protocols_Crew-accompanying ignition prevention and suppression resources and services _N/A_2021 | 288 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Grid Operations & Operating Protocols | 7.3.6 | Personnel work procedures and training in conditions of elevated fire risk |  | 3 | N/A | N/A | SCE_Grid Operations & Operating Protocols_Personnel work procedures and training in conditions of elevated fire risk _N/A_2021 | 289 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Grid Operations & Operating Protocols | 7.3.6 | Protocols for PSPS re-energization |  | 4 | N/A | N/A | SCE_Grid Operations & Operating Protocols_Protocols for PSPS re-energization _N/A_2021 | 290 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Grid Operations & Operating Protocols | 7.3.6 | PSPS events and mitigation of PSPS impacts |  | 5 | Customer Care Programs | PSPS-2 | SCE_Grid Operations & Operating Protocols_PSPS events and mitigation of PSPS impacts _PSPS-2_2021 | 294 | N/A | N/A | [8 empty] | Community Resource Centers (CRC): Adjust as needed. Community Resiliency Programs: Goals for Resilience Zones dependent on community leaders identifying potential customers. Targeting to obtain 5 to 10 agreements. Complete installation of microgrid islanding (CREI) capability on second pilot customer. Customer Resiliency Equipment: Critical Care Backup Battery (CCBB): Expand program to eligible MBL customers who are enrolled in CARE/ FERA and reside HFRA. Expand marketing and outreach plans. Well Water & Res Battery Station Rebates: Enhance the programs to increase customer participation by 20% - 40% | The refreshed CRC strategy for 2021 including evaluation of circuits that will likely be impacted by PSPS events -from the strategy/approach 12 communities have been identified that need CRC coverage (all of which have at least 1 CRC) Potential customer sites for participation in resiliency zones have been identified (the list includes 3 Tribal Nations); outreach to those potential customer sites have started Current efforts are underway to host PowerTalk webinars with the community-based organizations (CBO)/Faith-based organizations (FBOs) that are engaged with SCE’s Wildfire/PSPS preparedness initiative Tentative webinar dates to educate CBO/FBOs about CCBB program are scheduled for early Q2 | The refreshed CRC strategy for 2021 includes evaluation of circuits that will likely be impacted by PSPS events. The strategy identified 12 communities that need CRC coverage (all of which have at least 1 CRC) Community Resiliency Programs behind plan due to delays in identifying customers willing to participate; will continue to identify additional customer sites in Q3. Four customer agreements have been executed through Q2. CCBB program was completed in Q2 after reaching out to eligible Medical Baseline Customers and establishing additional partners (CBOs) Well Water & Residential Battery Station Rebate have 1,100 enrollments through Q2. | The refreshed CRC strategy for 2021 includes evaluation of circuits that will likely be impacted by PSPS events. 64 total CRC sites as of end of Q3. Community Resiliency Programs behind plan due to delays in identifying customers willing to participate; will continue to identify additional customer sites in Q4. Four customer agreements have been executed through Q3. Expecting to have a total of 8 resiliency zones to be in effect for fire season. CCBB program was completed in Q2 after reaching out to eligible Medical Baseline Customers and establishing additional partners (CBOs) Well Water & Residential Battery Station Rebate: Completed - ~1,800 enrollments through Q3. |  | Behind Plan, Likely to Meet Year-end Goal | SCE will continue to pursue community leaders to share potential customer sites | [6 empty] | Yes | In Review
SCE | 2021-11-02 | Grid Operations & Operating Protocols | 7.3.6 | Stationed and on-call ignition prevention and suppression resources and services |  | 6 | N/A | N/A | SCE_Grid Operations & Operating Protocols_Stationed and on-call ignition prevention and suppression resources and services _N/A_2021 | 302 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Data Governance | 7.3.7 | Centralized repository for data |  | 1 | Wildfire Safety Data Mart and Data Management (WiSDM / Ezy) | DG-1 | SCE_Data Governance_Centralized repository for data _DG-1_2021 | 303 | N/A | N/A | [8 empty] | WiSDM: Complete the WisDM solution analysis and design for centralized data repository Initiate staggered consolidation of datasets from SCE Enterprise systems Ezy Data: Implement the cloud platform infrastructure for Ezy Data Build a solution for data consumption, storage and visualization of inspection data (LiDAR, HD video, photograph) Enable an environment for Artificial Intelligence (AI) assisted analytics | SCE has completed the initial solution design for the Wildfire Safety Data Mart (WiSDM). Staggered consolidation of datasets will begin in Q3. The first release of the Ezy Data cloud platform was also completed in Q1. SCE is currently working on solutions to consume, store, and visualize data from wildfire inspection activities. | SCE has completed the initial solution design for the Wildfire Safety Data Mart (WiSDM). Staggered consolidation of datasets will begin in Q3. The first release of the Ezy Data cloud platform was also completed in Q1. SCE is continuing to work on solutions to consume, store, and visualize data from wildfire inspection activities. | Ezy Data is on track for meeting goal in Q4. WiSDM at-risk due to delays in initiating staggered consolidation of datasets to the centralized data repository from SCE Enterprise systems. Delays due to WiSDM architects reprioritized to work on initiatives mitigating PSPS risk in 2021 and also delayed due additional analysis being performed on which platform to proceed with in order to find the best solution WiSDM at-risk due to delays in initiating staggered consolidation of datasets to the centralized data repository from SCE Enterprise systems. Delays due to WiSDM architects reprioritized to work on initiatives mitigating PSPS risk in 2021 and also delayed due to additional analysis being performed on which platform to proceed with in order to find the best solution While this activity is at risk for not meeting its year end target, it is not intended to directly mitigate wildfire risk in 2021. |  | Behind Plan, At-Risk of Not Meeting Year-end Goal | Currently in negotiation with vendors to begin development, and goal completion will be contingent on length of time for contract completion and onboarding with vendor. . | [6 empty] | No
SCE | 2021-11-02 | Data Governance | 7.3.7 | Collaborative research on utility ignition and/or wildfire |  | 2 | N/A | N/A | SCE_Data Governance_Collaborative research on utility ignition and/or wildfire _N/A_2021 | 307 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Data Governance | 7.3.7 | Documentation and disclosure of wildfire-related data and algorithms |  | 3 | N/A | N/A | SCE_Data Governance_Documentation and disclosure of wildfire-related data and algorithms _N/A_2021 | 308 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Data Governance | 7.3.7 | Tracking and analysis of risk event data |  | 4 | N/A | N/A | SCE_Data Governance_Tracking and analysis of risk event data_N/A_2021 | 309 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Resource Allocation Methodology | 7.3.8 | Allocation methodology development and application |  | 1 | N/A | N/A | SCE_Resource Allocation Methodology_Allocation methodology development and application _N/A_2021 | 311 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Resource Allocation Methodology | 7.3.8 | Risk reduction scenario development and analysis |  | 2 | N/A | N/A | SCE_Resource Allocation Methodology_Risk reduction scenario development and analysis _N/A_2021 | 312 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Resource Allocation Methodology | 7.3.8 | Risk spend efficiency analysis |  | 3 | N/A | N/A | SCE_Resource Allocation Methodology_Risk spend efficiency analysis_N/A_2021 | 312 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Emergency Planning & Preparedness | 7.3.9 | Adequate and trained workforce for service restoration |  | 1 | SCE Emergency Response Training | DEP-2 | SCE_Emergency Planning & Preparedness_Adequate and trained workforce for service restoration _DEP-2_2021 | 313 | # trained | UAS (Unmanned Aircraft System): In 2021 SCE plans to expand the program by an additional 50 operators over 2020 levels. | UAS: 0 people to pass the FAA 107 exam in Q1. | UAS: Prepare 20 operators for the FAA 107 exam | UAS: Prepare 35 operators for the FAA 107 exam | UAS: Prepare 56 operators for the FAA 107 exam | UAS: In Q1 three additional operators passed the FAA 107 exam. While this activity is on track relative to its Q1 projected target, SCE is evaluating the current goal (50 additional operators passing the FAA 107 exam) and determining whether progress towards building in-house UAS capabilities is more appropriately tracked by other measures (e.g., advanced flight training and technical qualification standards). SCE notes that this UAS target focuses on building capabilities for emergent use cases and does not impact its ability to perform related WMP activities in 2021. SCE will notify WSD of any revisions in a future Change Orders report. | UAS: On Track - Nine operators have passed the FAA 107 exam. ~50 operators have attended FAA 107 prep courses in preparation of taking the exam in Q3 or Q4. | UAS: 2021 target is to train 56 employees (6 carryover from 2020 WMP and 50 new in 2021 WMP). Through Q3, 25 operators have taken and passed the FAA 107 exam |  | IMT (Incident Management Team): Have all PSPS IMT and Task Force members fully trained and qualified or requalified by July 1, 2021. | IMT: PSPS IMT trainings and qualifications began in Q1 and will continue throughout Q2. | IMT: Complete – PSPS IMT trainings and qualifications were completed in Q2. | IMT: Complete – PSPS IMT trainings and qualifications were completed in Q2. |  | Behind Plan, At-Risk of Not Meeting Year-end Goal | Planning additional webinars (not previously part of the UAS training program) to re-engage trainees who have not taken the FAA exam with the UAS training materials | [6 empty] | No
SCE | 2021-11-02 | Emergency Planning & Preparedness | 7.3.9 | Community outreach, public awareness, and communications efforts |  | 2 | N/A | N/A | SCE_Emergency Planning & Preparedness_Community outreach, public awareness, and communications efforts _N/A_2021 | 316 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Emergency Planning & Preparedness | 7.3.9 | Customer support in emergencies |  | 3 | N/A | N/A | SCE_Emergency Planning & Preparedness_Customer support in emergencies_N/A_2021 | 316 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Emergency Planning & Preparedness | 7.3.9 | Disaster and emergency preparedness plan |  | 4 | N/A | N/A | SCE_Emergency Planning & Preparedness_Disaster and emergency preparedness plan_N/A_2021 | 318 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Emergency Planning & Preparedness | 7.3.9 | Preparedness and planning for service restoration |  | 5 | N/A | N/A | SCE_Emergency Planning & Preparedness_Preparedness and planning for service restoration_N/A_2021 | 320 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Emergency Planning & Preparedness | 7.3.9 | Protocols in place to learn from wildfire events |  | 6 | N/A | N/A | SCE_Emergency Planning & Preparedness_Protocols in place to learn from wildfire events_N/A_2021 | 322 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Emergency Planning & Preparedness | 7.3.10 | Community engagement |  | 1 | Customer Education and Engagement - Community Meetings | DEP-1.2 | SCE_Emergency Planning & Preparedness_Community engagement_DEP-1.2_2021 | 324 | # of meetings | Host at least nine virtual community meetings. SCE will complete additional meetings as needed in 2021, based on PSPS impact to communities, up to 18 | 3 meetings | 6 meetings | 9 meetings | 9 meetings | Three community meetings were held by the end of Q1. | Nine community meetings were held by the end of Q2. | Nine virtual community meetings were held by the end of Q3. |  | N/A |  |  |  |  | Completed | [7 empty] | No
SCE | 2021-11-02 | Emergency Planning & Preparedness | 7.3.10 | Community engagement |  | 1 | Customer Education and Engagement, Marketing Campaign | DEP-1.3 | SCE_Emergency Planning & Preparedness_Community engagement_DEP-1.3_2021 | 331 | % PSPS awareness | PSPS Awareness goal: 50% | Greater than 50% | Greater than 50% | Greater than 50% | Greater than 50% | As of the end of Q1 PSPS awareness was at ~60%. | As of the end of Q2 PSPS awareness was at ~59%. | As of the end of Q3 PSPS awareness was at ~59%. |  | N/A |  |  |  |  | On Track | [7 empty] | No
SCE | 2021-11-02 | Emergency Planning & Preparedness | 7.3.10 | Community engagement |  | 1 | Customer Research and Education | DEP-4 | SCE_Emergency Planning & Preparedness_Community engagement_DEP-4_2021 | 333 | N/A | N/A | [8 empty] | Administer at least 4 PSPS-related surveys (PSPS Tracker Survey to capture feedback on the 2020 events, wildfire Community meeting feedback survey, CRC/CCV feedback survey, In-Language Wildfire Mitigation Communications Effectiveness Pre/Post Survey) | Began data collection for 2020 PSPS Tracker Survey in Q1. | Completed the data collection of residential and business customer feedback for the 2020 PSPS Tracker. Also completed the Residential report in Q2, and plan to complete the Business report in Q3. In-Language Wildfire Mitigation Communications Effectiveness Survey to begin in Q3. | Completed the Business report and began In-Language Wildfire Mitigation Communications Effectiveness Survey in Q3. Also began conducting surveys in Q3 for CRC/CCV activations for PSPS events, and plan to collect/aggregate feedback to date for CRC/CCV visitation surveys in Q4 (contingent upon PSPS events and deployment of resources). |  | On Track | [7 empty] | No
SCE | 2021-11-02 | Emergency Planning & Preparedness | 7.3.10 | Cooperation and best practice sharing with agencies outside CA |  | 2 | N/A | N/A | SCE_Emergency Planning & Preparedness_Cooperation and best practice sharing with agencies outside CA_N/A_2021 | 335 | N/A | N/A | [8 empty] | N/A
SCE | 2021-11-02 | Emergency Planning & Preparedness | 7.3.10 | Cooperation with suppression agencies |  | 3 | Aerial Suppression (DEP-5) | DEP-5 | SCE_Emergency Planning & Preparedness_Cooperation with suppression agencies_DEP-5_2021 | 337 | N/A | N/A | [8 empty] | Will enter a Memorandum of Understanding (MOU) with CAL FIRE and local county fire departments to provide standby cost funding for up to 5 aerial suppression resources strategically placed around the SCE service area. | SCE has submitted three MOUs to local counties for initial review. | All 3 MOUs have been signed by SCE and each respective county. Payments disbursed to all 3 counties in Q2. | All 3 MOUs have been signed by SCE and each respective county. Payments disbursed to all 3 counties in Q2. |  | Completed | [7 empty] | No
SCE | 2021-11-02 | Emergency Planning & Preparedness | 7.3.10 | Forest service and fuel reduction cooperation and joint roadmap |  | 4 | N/A | N/A | SCE_Emergency Planning & Preparedness_Forest service and fuel reduction cooperation and joint roadmap_N/A_2021 | 338 | N/A | N/A | [8 empty] | N/A
Notes:
On July 9, 2021, the California Public Utilities Commission (CPUC) issued a Proposed Decision (PD) on SCE’s 2021 GRC Track 1 request, which is expected to be voted on by August 19, 2021. Plans may vary pending SCE’s reevaluation after a final general rate case decision
In this QIU, SCE reports on progress in the 39 2021 WMP activities which were initiated to primarily address wildfire risks and/or PSPS impacts and which have specific 2021 program targets. SCE considers Non-WMP programs to be programs which are not initiated to primarily address wildfire risks and/or PSPS impacts. These programs are implemented for purposes primarily outside of wildfire / PSPS impact mitigation (e.g., for reliability), though they may provide indirect wildfire / PSPS impact mitigation benefits. Therefore, these programs would continue even if wildfire and/or PSPS risk did not exist.
Reported numbers are subject to revision upon data validation
NOTE: To add more rows, highlight the current last row of the table, copy, and paste directly below the last row
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: See notes at end of table below
Note on H1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SCE focuses its QIU on reporting on WMP activities which are initiated to primarily address wildfire risks and/or PSPS impacts and have specific program targets. SCE considers Non-WMP programs to be programs which are not initiated to primarily address wildfire risks and/or PSPS impacts. These programs are implemented for purposes primarily outside of wildfire / PSPS impact mitigation (e.g., for reliability), though they may provide indirect wildfire / PSPS impact mitigation benefits. Therefore, these programs would continue even if wildfire and/or PSPS risk did not exist. These programs can also include work SCE is doing as part of standard operations. Discussion on these programs were included in SCE’s 2020-2022 WMP.
Note on R28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This number may increase as more analysis is performed checking for previous work completions, and the remediation of actual pending notifications

## Initiative mapping-DO NOT EDIT (hidden)
WMP Table # / Category | WMP Initiative # | Initative activity | WMP category | WMP code | Utility
Risk Assessment and Mapping | 1 | A summarized risk map showing the overall ignition probability and estimated wildfire consequence along electric lines and equipment | Risk Assessment & Mapping | 7.3.1 | PGE
Risk Assessment and Mapping | 2 | Climate-driven risk map and modelling based on various relevant weather scenarios | Situational Awareness & Forecasting | 7.3.2 | SCE
Risk Assessment and Mapping | 3 | Ignition probability mapping showing the probability of ignition along the electric lines and equipment | Grid Design & System Hardening | 7.3.3 | SDGE
Risk Assessment and Mapping | 4 | Initiative mapping and estimation of wildfire and PSPS risk-reduction impact | Asset Management & Inspections | 7.3.4 | BVES
Risk Assessment and Mapping | 5 | Match drop simulations showing the potential wildfire consequence of ignitions that occur along the electric lines and equipment | Vegetation Management & Inspections | 7.3.5 | LU
Situational Awareness and Forecasting | 1 | Advanced weather monitoring and weather stations: | Grid Operations & Operating Protocols | 7.3.6 | PC
Situational Awareness and Forecasting | 2 | Continuous monitoring sensors | Data Governance | 7.3.7 | TBC
Situational Awareness and Forecasting | 3 | Fault indicators for detecting faults on electric lines and equipment | Resource Allocation Methodology | 5.3.4 | HWT
Situational Awareness and Forecasting | 4 | Forecast of a fire risk index, fire potential index, or similar | Emergency Planning & Preparedness | 7.3.9
Situational Awareness and Forecasting | 5 | Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions | Stakeholder Cooperation & Community Engagement | 7.3.10
Situational Awareness and Forecasting | 6 | Weather forecasting and estimating impacts on electric lines and equipment | Resource Allocation Methodology | 5.4
Situational Awareness and Forecasting | 7 | Forecast of a fire risk index, fire potential index, or similar
Situational Awareness and Forecasting | 8 | Personnel monitoring areas of electric lines and equipment in elevated fire risk conditions
Situational Awareness and Forecasting | 9 | Weather forecasting and estimating impacts on electric lines and equipment:
Situational Awareness and Forecasting | 10 | Weather forecasting and estimating impacts on electric lines and equipment:
Grid Design and System Hardening | 11 | Capacitor maintenance and replacement program
Grid Design and System Hardening | 12 | Circuit breaker maintenance and installation to de-energize lines upon detecting a fault
Grid Design and System Hardening | 13 | Covered conductor installation
Grid Design and System Hardening | 14 | Covered conductor installation
Grid Design and System Hardening | 15 | Covered conductor maintenance
Grid Design and System Hardening | 16 | Crossarm maintenance, repair, and replacement
Grid Design and System Hardening | 17 | Distribution pole replacement and reinforcement, including with composite poles
Grid Design and System Hardening | 18 | Expulsion fuse replacement
Grid Design and System Hardening | 19 | Grid topology improvements to mitigate or reduce PSPS events
Grid Design and System Hardening | 20 | Grid topology improvements to mitigate or reduce PSPS events
Grid Design and System Hardening | 21 | Installation of system automation equipment: installation of system automation equipment
Grid Design and System Hardening | 22 | Maintenance, repair, and replacement of connectors, including hotline clamps
Grid Design and System Hardening | 23 | Mitigation of impact on customers and other residents affected during PSPS event
Grid Design and System Hardening | 24 | Other corrective action
Grid Design and System Hardening | 25 | Pole loading infrastructure hardening and replacement program based on pole loading assessment program
Grid Design and System Hardening | 26 | Transformers maintenance and replacement
Grid Design and System Hardening | 27 | Transmission tower maintenance and replacement
Grid Design and System Hardening | 28 | Undergrounding of electric lines and/or equipment
Grid Design and System Hardening | 29 | Updates to grid topology to minimize risk of ignition in HFTDs
Grid Design and System Hardening | 30 | Updates to grid topology to minimize risk of ignition in HFTDs
Grid Design and System Hardening | 31 | Updates to grid topology to minimize risk of ignition in HFTDs
Asset Management and Inspections | 1 | Detailed inspections of distribution electric lines and equipment
Asset Management and Inspections | 2 | Detailed inspections of Transmission electric lines and equipment
Asset Management and Inspections | 3 | Improvement of Inspections
Asset Management and Inspections | 4 | Infrared inspections of distribution electric lines and equipment:
Asset Management and Inspections | 5 | Infrared inspections of transmission electric lines and equipment:
Asset Management and Inspections | 6 | Intrusive pole inspections (IPI)
Asset Management and Inspections | 7 | LiDAR inspections of distribution electric lines and equipment
Asset Management and Inspections | 8 | LiDAR inspections of transmission electric lines and equipment
Asset Management and Inspections | 9 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Asset Management and Inspections | 10 | Other discretionary inspection of distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Asset Management and Inspections | 11 | Other discretionary inspection of transmission electric lines and equipment, beyond inspections mandated by rules and regulations
Asset Management and Inspections | 12 | Patrol inspections of distribution electric lines and equipment
Asset Management and Inspections | 13 | Patrol inspections of transmission electric lines and equipment
Asset Management and Inspections | 14 | Pole loading assessment program to determine safety factor
Asset Management and Inspections | 15 | Quality assurance / quality control of inspections
Asset Management and Inspections | 16 | Substation inspections
Veg Management & Inspections | 1 | Additional efforts to manage community and environmental impacts
Veg Management & Inspections | 2 | Detailed inspections of vegetation around distribution electric lines and equipment
Veg Management & Inspections | 3 | Detailed inspections of vegetation around transmission electric lines and equipment
Veg Management & Inspections | 4 | Emergency response vegetation management due to red flag warning or other urgent conditions
Veg Management & Inspections | 5 | Fuel management and reduction of “slash” from vegetation management activities
Veg Management & Inspections | 6 | Fuel management and reduction of “slash” from vegetation management activities
Veg Management & Inspections | 7 | Improvement of inspections
Veg Management & Inspections | 8 | LiDAR inspections of vegetation around distribution electric lines and equipment
Veg Management & Inspections | 9 | LiDAR inspections of vegetation around transmission electric lines and equipment
Veg Management & Inspections | 10 | Other discretionary inspection of vegetation around distribution electric lines and equipment, beyond inspections mandated by rules and regulations
Veg Management & Inspections | 11 | Other discretionary inspection of vegetation around transmission electric lines and equipment, beyond inspections mandated by rules and regulations
Veg Management & Inspections | 12 | Patrol inspections of vegetation around distribution electric lines and equipment
Veg Management & Inspections | 13 | Patrol inspections of vegetation around transmission electric lines and equipment
Veg Management & Inspections | 14 | Quality assurance / quality control of inspections
Veg Management & Inspections | 15 | Recruiting and training of vegetation management personnel
Veg Management & Inspections | 16 | Remediation of at-risk species
Veg Management & Inspections | 17 | Removal and remediation of trees with strike potential to electric lines and equipment
Veg Management & Inspections | 19 | Removal and remediation of trees with strike potential to electric lines and equipment
Veg Management & Inspections | 20 | Substation inspections
Veg Management & Inspections | 21 | Substation vegetation management
Veg Management & Inspections | 22 | Vegetation inventory system
Veg Management & Inspections | 23 | Vegetation management to achieve clearances around electric lines and equipment
Grid Operations & Protocols | 1 | Automatic recloser operations
Grid Operations & Protocols | 2 | Crew-accompanying ignition prevention and suppression resources and services
Grid Operations & Protocols | 3 | Personnel work procedures and training in conditions of elevated fire risk
Grid Operations & Protocols | 4 | Protocols for PSPS re-energization
Grid Operations & Protocols | 5 | PSPS events and mitigation of PSPS impacts
Grid Operations & Protocols | 6 | Stationed and on-call ignition prevention and suppression resources and services
Data Governance | 1 | Centralized repository for data
Data Governance | 2 | Collaborative research on utility ignition and/or wildfire
Data Governance | 3 | Documentation and disclosure of wildfire-related data and algorithms
Data Governance | 4 | Tracking and analysis of risk event data
Resource Allocation Methodology | 1 | Allocation methodology development and application
Resource Allocation Methodology | 2 | Risk reduction scenario development and analysis
Resource Allocation Methodology | 3 | Risk spend efficiency analysis - not to include PSPS
Emergency Planning & Preparedness | 1 | Adequate and trained workforce for service restoration: SCE Emergency Response Training
Emergency Planning & Preparedness | 2 | Community outreach, public awareness, and communications efforts
Emergency Planning & Preparedness | 3 | Customer support in emergencies
Emergency Planning & Preparedness | 4 | Disaster and emergency preparedness plan
Emergency Planning & Preparedness | 5 | Preparedness and planning for service restoration
Emergency Planning & Preparedness | 6 | Protocols in place to learn from wildfire events
Stakeholder Cooperation & Community Engagement | 1 | Community engagement
Stakeholder Cooperation & Community Engagement | 2 | Community engagement
Stakeholder Cooperation & Community Engagement | 3 | Community engagement
Stakeholder Cooperation & Community Engagement | 4 | Cooperation and best practice sharing with agencies outside CA
Stakeholder Cooperation & Community Engagement | 5 | Cooperation with suppression agencies
Stakeholder Cooperation & Community Engagement | 6 | Forest service and fuel reduction cooperation and joint roadmap