## TUG Cost Forecast
TUG Cost Forecast
Difficulty | Description |  |  |  |  | Average Cost (2022$) Millions
Low | Typical setting: flat and rural areas -Straight/minimal bends, none to minimal re-routing required -Less civil construction due to existing infrastructure -Minimal paving and equipment -Low number of transformers per mile required |  |  |  |  | 1.15
Medium | Typical setting: medium density in residential/rural areas -Some curves, minimal to medium re-routing required -Moderate difficulty of civil construction -Moderate re-paving and equipment needed -Medium number of transformers per mile required |  |  |  |  | 2.89
High | Typical setting: rocky, hilly terrain and/or high population density -Rugged terrain, significant re-routing required (e.g., follow switchbacks, rear property, etc.) -Extensive difficulty of civil construction (e.g., horizontal directional drilling) -High number of transformers per mile required -High cost of restoration due to landscaping -City or county's work moratorium -Substation getaway construction required -Long lead times and permitting/construction difficulties around railroads and bridges -Large flood control channels/wash/culverts |  |  |  |  | 4.51
Infeasible | -Terrain or other parameters deem undergrounding construction infeasible (e.g., overhead directly above rocky mountains, not enough room to meet required clearances, etc.) |  |  |  |  | N/A
Note: The average unit cost per difficulty level is derived from internal cost estimators and planners.
Estimated Difficulty Level of Construction | 2024 | 2025 | 2026 | 2027 | 2028
Low | 63% | 10% | 0% | 0% | 0%
Medium | 37% | 90% | 29% | 35% | 44%
High | 0% | 0% | 71% | 65% | 56%
Level of Work | 2024 | 2025 | 2026 | 2027 | 2028 | Total
Primary Only Miles | 14.5 | 44 | 124 | 155 | 122 | 459.5
Primary and Secondary Miles | 5.5 | 16 | 26 | 45 | 48 | 140.5
Total Overhead Miles | 20 | 60 | 150 | 200 | 170 | 600
Secondary Only Miles | 0.5 | 1 | 2 | 5 | 4 | 12.5
Total Underground Miles (Rounded) | 20 | 65 | 180 | 240 | 200 | 705
Level of Work - Services | 2024 | 2025 | 2026 | 2027 | 2028 | Total
Number of Residential Meters | 271 | 498 | 1193 | 1594 | 2065 | 5621
Number of Non-Residential Meters | 84 | 151 | 372 | 419 | 544 | 1570
Total UG Services | 355 | 649 | 1565 | 2013 | 2609 | 7191
Residential Meter Relocation Projects
Work Order Number | Project Cost | Number of Meters | Approximate Cost Per Meter
TD986718 | 29480.66 | 3 | 9826.89
TD760689 | 5233.36 | 6 | 872.23
TD907546 | 156453 | 23 | 6802.3
TD800666 | 74072.68 | 9 | 8230.3
TD1131622 | 35237.01 | 10 | 3523.7
Total | 300476.71 | 51 | 5891.7002
Commercial Meter Relocation Projects
Work Order Number | Project Cost | Number of Meters | Approximate Cost Per Meter
TD1043552 | 126372.65 | 7 | 18053.24
TD616022 | 128547.23 | 6 | 21424.54
Total | 254919.88 | 13 | 19609.2215
| 2024 | 2025 | 2026 | 2027 | 2028 | Assumptions
Cost to UG Primary Only Miles | 26972.4737 | 130259.36 | 586653.2008 | 712007.225 | 535526.7104 | Easy miles has no re-routes; Medium difficulty has 10% re-route; High difficulty has 20% re-route
Cost to UG Co-located Primary and Secondary Miles | 11765.579 | 54472.096 | 141459.1186 | 237718.5412 | 242303.8886
Cost to UG Secondary Only Miles | 930.0853 | 2960.44 | 9462.1484 | 22967.975 | 17558.2528
Cost to UG Services | 3243.8254 | 5895.0591 | 14323.4287 | 17607.6339 | 22833.7774
Total UG Costs ($000) | 42911.9634 | 193586.9551 | 751897.8965 | 990301.3752 | 818222.6293
Weighted Unit Cost ($2022) ($000) | 2145.5982 | 4020.4509
| 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | Total
UG Miles | 11 | 20 | 65 | 180 | 240 | 200 | 716
Unit Cost (2022$) ($000) | 2145.5982 | 2145.5982 | 4020.4509 | 4020.4509 | 4020.4509 | 4020.4509 | N/A
Escalation | 1.0538 | 1.106 | 1.1329 | 1.1425 | 1.1505 | 1.1672 | N/A
Sub-total | 24872.1237 | 47460.3741 | 296071.7323 | 826815.1323 | 1110127.8632 | 938570.2386 | 3243917.4643
Environmental 3% | 746.1637 | 1423.8112 | 8882.152 | 24804.454 | 33303.8359 | 28157.1072 | 97317.5239
Total Cost (Nominal $000) | 25618.2874 | 48884.1853 | 304953.8843 | 851619.5863 | 1143431.6991 | 966727.3458 | 3341234.9882
Targeted Undergrounding | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | Total
Forecast Circuit Miles (OH Miles) | 11 | 20 | 60 | 150 | 200 | 170 | 611
Forecast Circuit Miles (UG Miles) | 11 | 20 | 65 | 180 | 240 | 200 | 716
Forecast Cost (Nominal $000s) | 25618.2874 | 48884.1853 | 304953.8843 | 851619.5863 | 1143431.6991 | 966727.3458 | 3341234.9882
Targeted Undergrounding | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | Total
Forecast Circuit Miles (OH Miles) | 11 | 20 | 60 | 150 | 200 | 170 | 611
Forecast Circuit Miles (UG Miles) | 11 | 20 | 70 | 175 | 240 | 205 | 721
Forecast Cost (Nominal $000s) | 42354.4046 | 80819.6319 | 324528.9335 | 818174.151 | 1129912.4595 | 979179.7845 | 3374969.3649
| 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | Total
UG Miles | 11 | 20 | 70 | 175 | 240 | 205 | 721
Unit Cost (2022$) ($000) | 3547.2915 | 3547.2915 | 3972.9155 | 3972.9155 | 3972.9155 | 3972.9155 | N/A
Escalation | 1.0538 | 1.106 | 1.1329 | 1.1425 | 1.1505 | 1.1672 | N/A
Sub-total | 41120.7811 | 78465.662 | 315076.6345 | 794343.8359 | 1097002.3879 | 950659.985 | 3276669.2863
Environmental 3% | 1233.6234 | 2353.9699 | 9452.299 | 23830.3151 | 32910.0716 | 28519.7995 | 98300.0786
Total Cost (Nominal $000) | 42354.4046 | 80819.6319 | 324528.9335 | 818174.151 | 1129912.4595 | 979179.7845 | 3374969.3649